## GanttChart
[Aircraft Boarding Simulation] Project Schedule
[Singapore University of Technology & Design]
| Project Start Date | 2018-09-17 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
| Project Lead | Karthic Harish | [6 empty] | 2018-09-17 | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15 | [6 empty] | 2018-10-22 | [6 empty] | 2018-10-29 | [6 empty] | 2018-11-05 | [6 empty] | 2018-11-12 | [6 empty] | 2018-11-19 | [6 empty] | 2018-11-26 | [6 empty] | 2018-12-03
 | time axis 2018-09-17 to 2018-12-09
WBS | TASK | Karthic Harish | Ivan Zhou Yue | START | END | DAYS | % DONE | WORK DAYS | time axis 2018-09-17 to 2018-12-09
1 | [Background Research] |  |  |  | - |  |  | -
1.1 | [Project Description] |  |  | 2018-09-17 | 2018-09-18 | 2 | 100% | 2
1.2 | [Problem Area and Motivation] |  |  | 2018-09-19 | 2018-09-20 | 2 | 100% | 2
1.3 | [Mapping Project Timeline] |  |  | 2018-09-21 | 2018-09-22 | 2 | 100% | 1
1.4 | [Researching 3 Boarding Strategies] |  |  | 2018-09-23 | 2018-09-25 | 3 | 100% | 2
1.4.1 | [Random Boarding] |  |  | 2018-09-26 | 2018-09-26 | 1 | 100% | 1
1.4.2 | [Back-To-Front Boarding] |  |  | 2018-09-27 | 2018-09-27 | 1 | 100% | 1
1.4.3 | [Outside-In Boarding] |  |  | 2018-09-28 | 2018-09-28 | 1 | 100% | 1
1.5 | [Researching Parameters] |  |  | 2018-09-29 | 2018-10-03 | 5 | 100% | 3
2 | [Formulation] |  |  |  | - |  |  | -
2.1 | [Performance Measure] |  |  | 2018-10-03 | 2018-10-03 | 1 | 100% | 1
2.2 | [Simulation Design] |  |  | 2018-10-04 | 2018-10-07 | 4 | 100% | 2
2.2.1 | [Programming Logic Flowchart] |  |  | 2018-10-08 | 2018-10-09 | 2 | 100% | 2
2.2.2 | [State Machine Diagram] |  |  | 2018-10-10 | 2018-10-11 | 2 | 100% | 2
2.2.3 | [Understanding JavaScript] |  |  | 2018-10-12 | 2018-10-17 | 6 | 100%
2.3 | [Formulate the models in pseudo-code] |  |  | 2018-10-18 | 2018-10-23 | 6 | 100% | 4
3 | [Modelling and Simulation] |  |  |  | - |  |  | -
3.1 | [Implement pseudo-code on JavaScript & Debugging] |  |  | 2018-10-24 | 2018-11-01 | 9 | 100% | 7
3.1.1 | [Random Boarding] |  |  | 2018-11-01 | 2018-11-03 | 3 | 100% | 2
3.1.2 | [Back-To-Front Boarding] |  |  | 2018-11-03 | 2018-11-05 | 3 | 100% | 1
3.1.3 | [Outside-In Boarding] |  |  | 2018-11-05 | 2018-11-07 | 3 | 100% | 3
3.2 | [Tabulate test results] |  |  | 2018-11-07 | 2018-11-08 | 2 | 100% | 2
3.3 | [Construct guided visual tour of screenshots & video featuring various test cases] |  |  | 2018-11-09 | 2018-11-18 | 10 | 100% | 6
3.4 | [Refining Model Aesthetics] |  |  | 2018-11-19 | 2018-11-22 | 4 | 100% | 4
4 | [Statistics Output Analysis] |  |  |  | - |  |  | -
4.1 | [Gather Statistics & construct tests] |  |  | 2018-11-23 | 2018-11-26 | 4 | 100% | 2
4.1.1 | [Hypothesis Testing on average time] |  |  | 2018-11-27 | 2018-11-28 | 2 | 100% | 2
5 | [Conclusion] |  |  |  | - |  |  | -
5.1 | [Cleaning up Documents] |  |  | 2018-11-29 | 2018-12-02 | 4 | 100% | 2
5.2 | [Bibliography] |  |  | 2018-12-03 | 2018-12-03 | 1 | 100% | 1
5.3 | [HTML documents] |  |  | 2018-12-04 | 2018-12-05 | 2 | 100% | 2
-
-